## Read Me
LMX OS Roadmap — User Story Mapping
Companion to docs/ROADMAP.md — every tracked item (B/E/S/D/A/C/P/F/I/T), each with a status and a user story.
How to use this sheet
Go to the 'User Stories' tab. Use the filter arrows on the header row to narrow by Section, Status, or Phase. Sort by ID to follow the roadmap's own ordering within a section.
Status key
Done — shipped and in the codebase today.
Partial — some of it is built; the rest is named explicitly rather than assumed done.
Open — not started.
Deliberately not building / Superseded — a considered no (or replaced by a newer item), kept here so the decision has a record.
Source
docs/ROADMAP.md, as of the July 2026 competitive-analysis and P7 updates. If the roadmap changes, this sheet should be regenerated from it rather than hand-edited out of sync.

## User Stories
ID | Section | Feature | Status | Phase | User Story
B1 | Business/org | Hire the senior backend engineer | Open | Pre-Phase 4 (parallel enabler) | As LMX's CTO, I want to hire a senior backend engineer, so that engineering capacity isn't a single point of failure and Phases 4-7 can run in parallel instead of one at a time.
B2 | Business/org | Sign the first client contract | Open | Gate for Phase 9 | As LMX's business development lead, I want to sign the first client contract, so that the 2.5 DPH assumption and the Epicor payload mapping get validated against real orders instead of demo data.
B3 | Business/org | Get access to the Source of Truth Index | Open | Gates E4 | As the engineer who built the batch-hold and SLA logic, I want access to the canonical LMX OS Brief documents, so that the 4-question decision logic and hold-window minutes are verified against the real spec instead of a reconstructed summary.
B4 | Business/org | Choose a payroll provider | Done - Rippling decided | Phase 7 | As LMX's founding team, we want to choose a single payroll and tax provider, so that driver pay and tax compliance run through one accountable system instead of being improvised per hire.
B5 | Business/org | Provision a real Twilio account + phone number | Open | Pre-Phase 5/6 | As the ops team, I want a real Twilio account and phone number provisioned, so that OTP codes and masked customer/support SMS actually send instead of only being logged by a stub.
W1 | Workflow gaps | Returns & core pickups as first-class work | Open | Phase 6 | As a shop owner, I want the driver to collect my tagged cores and returns during the delivery stop and confirm what was taken, so that my credits move as fast as my parts - and as a driver, I want those pickups to appear as real route stops with an item list, so that every kind of work I do is counted work.
W2 | Workflow gaps | COD collection & payment disputes | Open | Phase 6 | As a driver facing a customer who disputes the charge at the door, I want one tap to escalate to the distributor so I can keep moving, so that I never negotiate money on a doorstep - and as a distributor owner, I want accounts with repeated disputes surfaced monthly, so that I resolve money problems in my office, not at my customers' doors.
W3 | Workflow gaps | SLA-breach invoice credits | Open | Phase 8 follow-up | As a distributor owner, I want contractually defined invoice credits when SLA thresholds are breached, so that my delivery vendor is paid for outcomes rather than effort.
W4 | Workflow gaps | Driver-visible scorecard | Open | Phase 10 (with I4) | As a driver, I want to see my own numbers in the same view and with the same definitions the company uses, so that the scorecard reads as a shared standard rather than a camera pointed at me.
W5 | Workflow gaps | Counter-person order status lookup | Open | Phase 8 follow-up | As a counter person, I want to look up any order's live status and ETA by shop name or order number, so that the rare status question takes ten seconds instead of a radio call.
W6 | Workflow gaps | Orchestrator-editable urgency configuration | Open | No dependency | As the orchestrator, I want to adjust part-type urgency rules myself in configuration, so that 'body panels are never urgent' doesn't require a developer and a deploy.
W7 | Workflow gaps | Training-data rights in the customer contract | Open - gates B2 | Now (legal) | As LMX leadership, I want model-training rights, cross-customer aggregation rights, and anonymization terms written into customer #1's contract before the first delivery, so that the data the operation generates is usable for the learning loop without a later amendment.
W8 | Workflow gaps | Epicor staging-module qualification check | Open | Now (sales process) | As LMX's sales lead, I want to ask whether a prospect's Epicor runs a warehouse/staging module before signing, so that we know whether real-time ingestion is even possible for that customer rather than discovering it after the contract.
W9 | Workflow gaps | Shadow-mode comparison engine & cutover scorecard | Open | Phase 9 | As a distributor owner, I want LMX OS to run alongside my existing dispatch on my real orders for a few weeks before cutover, so that I see the performance gap on my own volume before I commit - measured on nine metrics with the divergent orders examined individually, not just the aggregates.
W10 | Workflow gaps | Package identity & scan-at-pickup verification | Open - design decision pending | Phase 6 (with A2) | As a driver picking up at the warehouse, I want to scan each package and have the system confirm it matches the order I am carrying, so that a wrong part is caught before I drive across town instead of at the shop's door - and as a distributor owner, I want a verifiable record of exactly which packages left the building and which were handed over, so that 'it never arrived' and 'that's not what I ordered' both have an answer.
R1 | Risk & compliance | Insurance & liability plan | Open - gates Phase 9 | Start now (business/legal) | As LMX leadership, I want commercial auto, cargo, and general liability coverage in place before drivers carry real packages, so that a single accident or lost shipment is an insured event rather than a company-ending liability.
R2 | Risk & compliance | Driver background checks & MVR screening | Open - gates Phase 9 | Start now (business/legal) | As LMX leadership, I want every driver background-checked and their motor-vehicle record screened before their first shift, so that we know a driver is safe to put on the road - document expiry tracking alone doesn't tell us that.
R3 | Risk & compliance | Privacy policy & data-handling/retention policy | Open - gates Phase 9 | Start now (business/legal) | As a customer whose name, address, and phone number LMX stores, I want a published policy saying what happens to my data and how I can have it deleted, so that my information is handled accountably - and so LMX can answer an enterprise client's security questionnaire.
R4 | Risk & compliance | Driver document upload pipeline | Open | Phase 6 (with A3) | As LMX's onboarding staff, I want drivers to upload real license and insurance documents through the app, so that compliance evidence is a verified file on record rather than whatever text string was typed into the field.
R5 | Risk & compliance | Failed-delivery / redelivery workflow | Open | Phase 4 | As a hub dispatcher facing a refused package, wrong address, or closed shop, I want a defined path for what happens next - redelivery, client notification, billing adjustment - so that a failed order gets resolved instead of sitting in a dead-end status forever.
R6 | Risk & compliance | Hub closure / holiday calendar | Open | Phase 4 | As a hub ops manager, I want to mark days the hub isn't operating, so that the nightly learning job and the dispatch optimizer don't plan routes for a hub that's closed for a holiday or weather event.
E1 | Core backend | Verify Google Route Optimization against a live project | Open | Phase 4 | As a hub dispatcher relying on the optimizer, I want the Google Route Optimization integration verified against a real API call, so that I can trust the routes it proposes instead of an unverified request/response mapping.
E2 | Core backend | Tune SLA_TIER_SKIP_PENALTY values | Open | Phase 4 / I5 | As a hub dispatcher, I want the SLA tier skip penalties tuned to real route economics, so that the optimizer's tier prioritization reflects actual cost tradeoffs instead of a placeholder ordering.
E3 | Core backend | Confirm real Epicor payload field names | Open | Phase 4 (needs B2) | As the engineer integrating with a client's Epicor system, I want the real payload field names confirmed against a live tenant, so that orders ingest correctly instead of failing on a guessed schema.
E4 | Core backend | Verify the batch-hold 4-question decision logic | Open | Phase 4 (needs B3) | As a hub dispatcher, I want the batch-hold decision logic verified against the canonical spec, so that commingling decisions match the intended design rather than a reconstructed interpretation.
E5 | Core backend | Recalibrate SLA hold-window minutes | Open | Phase 4 / I5 | As a hub dispatcher, I want the SLA hold-window minutes recalibrated from real Hub 1 data, so that orders are held just long enough to batch efficiently without risking an SLA breach.
E6 | Core backend | Confirm Learning Loop flag-type naming convention | Open | Phase 4 | As the engineer building the annotation loop, I want the flag-type naming convention signed off by a driver-app stakeholder, so that the contract between driver annotations and the Learning Loop isn't just an internal guess.
E7 | Core backend | Wire a real scheduler for the Learning Loop's nightly job | Done | Phase 4 | As a hub, I want the Learning Loop's nightly detection job to run automatically on schedule, so that rule proposals get generated every night without anyone manually triggering it.
E8 | Core backend | Move the event bus off in-process | Done | Phase 5 | As the platform running on more than one instance, I want the event bus backed by Redis instead of in-process memory, so that hold-release and dispatch events stay consistent across multiple app instances.
E9 | Core backend | Validate the 2.5 DPH figure | Open | Phase 9 (needs B2) | As LMX leadership, I want the 2.5 deliveries-per-hour assumption validated against real Hub 1 data, so that pricing and staffing decisions rest on a proven number instead of a model assumption.
E10 | Core backend | Tune HOT_SHOT's skip-penalty/hold-window placeholders | Open | Phase 8 follow-up / I5 | As a hub dispatcher, I want HOT_SHOT's skip-penalty and hold-window values calibrated like the other tiers, so that the premium tier's priority handling is based on real economics, not a guess.
S1 | Security | Real per-user authentication for the ops dashboard | Done | Phase 5 | As a hub ops manager, I want each staff member to log in with their own account and role, so that I know who did what in the dashboard and can limit admin actions to admins.
S2 | Security | Secrets management | Open | Phase 5 | As the engineering team, I want credentials stored in a real secrets manager instead of a .env file, so that a leaked file or repo doesn't hand over database passwords and API keys.
S3 | Security | A real production hosting decision | Open | Phase 5 | As the engineering team preparing for Hub 1, I want a resilient hosting setup instead of a single-instance docker-compose, so that a container crash or server failure doesn't take down dispatch for real drivers and orders.
S4 | Security | Observability | Partial | Phase 5 | As an on-call engineer, I want error tracking and alerting layered on top of the existing metrics, so that I find out about a production problem from a page, not from a driver's phone call.
S5 | Security | General API rate limiting | Done | Phase 5 | As the platform, I want a per-IP rate limit across the whole API, so that abusive traffic or credential-guessing can't overwhelm the system before authentication even runs.
S6 | Security | A real security review | Open | Phase 5 | As LMX leadership, I want an outside security review of the platform, so that real orders, drivers, and eventually payments aren't the first real test of its defenses.
S7 | Security | Twilio inbound-webhook signature verification | Done | Phase 5 | As the platform receiving inbound SMS webhooks, I want Twilio's signature verified on every request, so that a forged webhook can't inject fake driver replies into the system.
S8 | Security | Rate-limit client login | Done | Phase 5 | As a client company logging into the portal, I want login attempts rate-limited, so that someone else can't brute-force my company's portal password.
S9 | Security | Enforce distinct client/driver JWT secrets at startup | Done | Phase 5 | As the platform, I want the client and driver JWT secrets to be provably different at startup, so that a token issued for one audience can never be replayed as if it were the other.
D1 | Ops dashboard | Add a list-hubs endpoint | Done | - | As a hub ops staff member, I want to pick my hub from a real dropdown instead of typing a UUID, so that I can't accidentally point the dashboard at the wrong hub.
D2 | Ops dashboard | Stop baking the API URL in at Docker build time | Done | - | As the engineer deploying the dashboard, I want the API URL configured at container start instead of baked in at build time, so that one built image can point at any environment without a rebuild.
A1 | Driver app | Push notifications | Open | Phase 6 | As a driver, I want a push notification the moment a new job is offered to me, so that I don't have to keep the app open and polling to catch new work.
A2 | Driver app | Real camera/barcode scanning | Open | Phase 6 | As a driver scanning parcels at pickup, I want to scan a real barcode, so that the parcel count is accurate instead of a manual tap anyone could get wrong or fake.
A3 | Driver app | Real photo/signature capture + upload pipeline | Open | Phase 6 | As a driver completing a delivery, I want to actually capture and upload a photo or signature, so that proof of delivery is a real image on file, not a placeholder URL.
A4 | Driver app | A real PIN-issuance/verification system | Open | Phase 6 | As a driver delivering an order that requires a PIN, I want the PIN checked against a real system, so that I can be confident the person receiving the package is who they say they are.
A5 | Driver app | Maps SDK / turn-by-turn navigation | Open | Phase 6 | As a driver on route, I want live turn-by-turn navigation in the app, so that I don't need a separate maps app to find each stop.
A6 | Driver app | Mobile app store deployment pipeline | Open | Phase 6 | As a driver, I want to install the app from TestFlight or the Play Store, so that I don't need developer tooling just to get the app on my phone.
A7 | Driver app | Masked voice calling | Open | Phase 6 | As a driver or customer who needs to talk instead of text, I want a masked voice call option, so that we can resolve an issue quickly without exposing either party's real phone number.
A8 | Driver app | Harden inbound-SMS reply matching | Done | Phase 6 | As a shop replying to a delivery SMS, I want my reply matched to the correct, active conversation, so that my message doesn't get attached to the wrong or already-completed stop.
A9 | Driver app | Real earnings formula + payroll integration | Partial (scaffolding shipped) | Phase 7 | As a driver, I want my earnings screen to show a real, calculated number tied to actual payroll, so that I know what I'll actually be paid instead of seeing a placeholder.
C1 | Components | Client-facing dashboard | Done (Phase 8) | - | As a client company, I want a portal showing my order history, status, and fees, so that I don't have to call LMX to know where my orders stand.
C2 | Components | Shop SMS | Done (Phase 8) | - | As a shop, I want an automatic text when my order is picked up and when the driver's en route, so that I don't have to guess or call in to check.
C3 | Components | A real billing/invoicing system | Partial | Phase 8 follow-up | As a client company, I want a real monthly statement and invoice I can download, so that I can reconcile what I owe LMX without manually recomputing it from order history.
C4 | Components | Multi-user client accounts | Open (deliberate, later) | Phase 8 follow-up | As a client company with both an AP contact and an ops contact, I want more than one login for my company, so that each person can access the portal without sharing one password.
C5 | Components | Self-service client signup | Deliberately not building | - | As LMX's business development team, we deliberately do not want a self-serve client signup flow, so that every new client relationship stays a real onboarding conversation, matching a B2B operator model rather than self-serve SaaS.
P1 | Autonomy partners | Courier abstraction over the fleet model | Open | Phase 11 (Track A gate) | As the engineering team, I want the fleet model generalized into a courier abstraction (human driver, autonomy partner, or gig courier), so that adding a new capacity type later doesn't require reworking code that assumes every courier is a person.
P2 | Autonomy partners | Capacity-provider adapter layer | Open | Phase 11 (Track A gate) | As the engineering team, I want one adapter per capacity partner normalizing capacity, assignment, and status, so that onboarding a new autonomy or gig partner doesn't mean writing bespoke dispatch logic each time.
P3 | Autonomy partners | Mode-aware dispatch | Open | Phase 11 | As a hub dispatcher, I want the optimizer to filter and choose the cheapest eligible delivery mode per order, so that a 40lb order never gets offered to a bike courier and cost-per-drop stays optimized across every available mode.
P4 | Autonomy partners | Unmanned handoff + proof of delivery | Open | Phase 11 (shares A4) | As a shop receiving an autonomous vehicle for pickup, I want a clear load-confirmation flow, so that handing off a parcel to a bot is as unambiguous as handing it to a driver.
P5 | Autonomy partners | Partner settlement | Open | Phase 11 (later) | As an autonomy or gig-courier partner, I want a monthly settlement statement for the deliveries I carried, so that I get paid accurately without a manual reconciliation with LMX.
P6 | Autonomy partners | Partner portal | Open | Phase 11 (later) | As an autonomy or gig-courier partner, I want a portal showing my delivery history and settlement statements, so that I can check my own performance and pay without emailing LMX ops.
P7 | Autonomy partners | Gig-courier cost-optimized dispatch | Open (gated on unit economics) | Phase 11 (Track B) | As LMX leadership, I want the option to route an order to a gig courier when it's genuinely the cheaper eligible choice, so that capacity can flex without ever changing the client's brand, SLA, or bill - capped and tagged so it never masks LMX's own unit economics.
F1 | Competitive gaps | Live driver location pipeline | Open | Phase 6 | As the platform, I want the driver app to periodically report its location, so that there's a real, current position on file for every driver on shift.
F2 | Competitive gaps | Live map view (ops dashboard) | Open | Phase 6 | As a hub ops manager, I want to see every driver's live position on a map, so that I know where my fleet actually is, not just what stop list each driver was assigned.
F3 | Competitive gaps | Customer-facing live tracking page | Open | Phase 8 follow-up | As the person receiving a delivery, I want a link that shows my driver's live position and ETA, so that I don't have to call the shop or guess when my part will arrive.
F4 | Competitive gaps | Outbound status webhooks + integrations surface | Open | Phase 8 follow-up | As a client's system administrator, I want to subscribe to order status webhooks, so that my own systems update automatically instead of polling or waiting on a manual check.
F5 | Competitive gaps | Flexible/rate-table billing | Open | Phase 8 follow-up | As a client with orders of very different sizes, I want billing that can reflect piece count, weight, or mileage, not just a flat per-drop rate, so that pricing matches the actual cost of serving my orders.
F6 | Competitive gaps | Real-time mid-route re-optimization | Open | Phase 4 (needs E1) | As a hub dispatcher, I want the optimizer to re-sequence an in-progress route when conditions change, so that a driver isn't stuck following a plan that's gone stale since the last cycle.
F7 | Competitive gaps | Client- and ops-facing analytics dashboards | Open | Phase 10 (folds into I4) | As a client company, I want to see my own on-time rate, volume, and cost trend in the portal, so that I have concrete proof of the value of switching to per-drop pricing with LMX.
F8 | Competitive gaps | White-label / multi-brand portal theming | Open | Phase 8 follow-up | As a reselling partner, I want the client portal to carry my own brand, so that my customers experience it as part of my business, not a visibly third-party tool.
F9 | Competitive gaps | Hybrid gig-fleet overflow dispatch | Superseded -> reinstated as P7 | - | Superseded: see P7 for the current, generalized version of this story (LMX leadership routing to the cheapest eligible capacity, including gig couriers).
F10 | Competitive gaps | A real path to SOC 2 (or equivalent) certification | Open | Phase 5 | As an enterprise client's security team, I want to see a SOC 2 report before signing, so that I have independent assurance LMX handles data and access responsibly.
F11 | Competitive gaps | SSO/SAML for ops and client logins | Open | Phase 5 | As an enterprise client's IT admin, I want to enforce SSO for anyone accessing the portal, so that portal access follows the same identity policy as the rest of my company's tools.
F12 | Competitive gaps | Network/territory optimization tooling | Open | Later, multi-hub | As LMX leadership planning a second or third hub, I want tooling to redesign depot/zone boundaries, so that expansion decisions are based on a real optimization model instead of intuition.
F13 | Competitive gaps | Ratings & feedback capture | Open | Phase 8 follow-up | As a shop after a delivery, I want to leave a quick rating and comment, so that LMX knows how the delivery actually went, not just whether the status says completed.
F14 | Competitive gaps | Orchestrator route-preview / shadow mode | Open | Phase 9 | As a hub dispatcher during the pilot, I want to preview the optimizer's proposed plan and override it if needed, so that I can build trust in autonomous dispatch before relying on it fully.
I1 | Intelligence layer | Ground-truth event capture | Open | Phase 10 (pre-pilot) | As the Learning Loop, I want real delivered/arrived timestamps and decline/hold-release data captured, so that there's actual ground truth to learn from instead of a proxy that was never meant for this.
I8 | Intelligence layer | Manual capture of non-default training situations | Open | Phase 3.5 / Phase 9 | As whoever runs Hub 1 operations, I want a checklist of the training situations that aren't captured automatically - the paired access-note comparison, the dispatcher gut-call log, the scaffold-era call tally, the shadow divergence pairs - so that the third of the training matrix that needs a human to write it down actually gets written down, including two things only capturable before cutover.
I2 | Intelligence layer | Rule review & promotion flow | Open | Phase 10 (pre-pilot) | As a hub ops manager, I want to review and approve or dismiss a proposed rule change from the Learning Loop, so that per-shop overrides get vetted by a person before they take effect.
I3 | Intelligence layer | Broaden the annotation vocabulary | Open | Phase 10 (pre-pilot) | As a driver, I want to flag more than just hold-window issues (parking, gate codes, shop prep slowness), so that what I know about a shop becomes part of the system instead of staying in my head.
I4 | Intelligence layer | Descriptive analytics on the captured truth | Open | Phase 10 (during/after pilot) | As a hub ops manager, I want DPH, SLA hit rate, and hold-window effectiveness reported per driver/hub/day, so that I can see how the operation is actually performing, not just whether the day went fine.
I5 | Intelligence layer | Calibration from data | Open (=E2/E5/E9/E10) | Phase 10 (during/after pilot) | As LMX leadership, I want skip penalties, hold windows, and the DPH figure retuned from real data, so that every placeholder number gets replaced with something proven.
I6 | Intelligence layer | Predictive models | Open (data-gated) | Phase 10 (later) | As a hub dispatcher, I want the optimizer to use predicted ETAs and per-shop service times instead of static estimates, so that routes reflect what's actually likely to happen, not a fixed assumption.
I7 | Intelligence layer | Ops copilot | Open (needs LLM API key) | Phase 10 (later) | As a hub ops manager, I want to ask a natural-language question like 'why was yesterday slow?' and get a real answer from the system's own data, so that I don't have to manually dig through dashboards to explain a bad day.
T1 | Testing/process | Load/performance test against the design budget | Done | Phase 9 | As the engineering team, I want the optimizer load-tested against the design budget (20 drivers/100 orders/<5s), so that we know the dispatch cycle holds up before it's carrying real orders.
T2 | Testing/process | Local sandbox can't fully exercise Redis rate limiting | Documented, not a bug | - | As the engineering team, I want it documented that the sandbox's test Redis can't exercise EXPIRE...NX the way production Redis does, so that this known limitation doesn't get 'rediscovered' and mistaken for a real bug.